## Backlog
Story ID | Epic / Module | Type | User Story (As a ... I want ... so that ...) | Acceptance Criteria | Priority | Points | Sprint | Status | Owner | Depends On | Risk | Tasks | Est (h) | Actual (h) | Remain (h) | Progress | Demo in review | Note
US-01 | Auth |  | As a visitor, I want to register a learner or instructor account so that I can access the platform. | Email + password validated; a verification email is sent; a user can hold both learner and instructor roles (FR-AUTH-03). | Must | 8 | Sprint 1 | done | DuongNT182 | [7 empty] | Yes
US-02 | Auth |  | As a registered user, I want to log in and get role-based access so that I can use the features for my role. | Correct credentials return a session/JWT; role drives authorization; account locks 30 min after 5 wrong tries. | Must | 8 | Sprint 3 | done | DuongNT182 | US-01 | [6 empty] | Yes
US-03 | Auth |  | As a user, I want to sign in with Google/Facebook so that I do not manage another password. | OAuth login creates or links an account; a returning OAuth user lands logged in. | Should | 5 | Sprint 4 | todo | DuongNT182 | US-01 | [6 empty] | Yes
US-04 | Auth |  | As a signed-in user, I want to view and edit my profile so that my account details stay current. | View profile; edit name/avatar; change password with a current-password check. | Should | 5 | Sprint 2 | done | DuongNT182 | US-02 | [6 empty] | Yes
US-05 | Course Authoring |  | As an instructor, I want to create and edit a course and set its price so that I can publish it for sale. | Course CRUD with title/description/thumbnail/price; draft vs published state; only the owner can edit. | Must | 8 | Sprint 2 | done | TienPQ9 | US-01 | [6 empty] | Yes
US-06 | Course Authoring |  | As an instructor, I want to add and edit multi-format lessons (video, text, file) so that my course has real content. | Lessons ordered within sections; video stored by storage_key not a public URL; add/edit/delete lesson. | Must | 13 | Sprint 2 | done | TienPQ9 | US-05 | [6 empty] | Yes
US-07 | Quiz |  | As an instructor, I want to create a quiz for a lesson so that learners can test themselves. | Quiz with questions/options and a correct answer; attached to a lesson. | Should | 5 | Sprint 3 | done | DuongNT182 | US-06 | [6 empty] | Yes
US-08 | Instructor |  | As an instructor, I want to manage the courses I have published so that I can keep them up to date. | List own courses with status; unpublish/republish; see enrollment count. | Should | 3 | Sprint 2 | done | DuongNT182 | US-05 | [6 empty] | Yes
US-09 | Instructor |  | As an instructor, I want to see my revenue so that I know how my courses perform. | Revenue per course and total, from completed (paid) orders only. | Could | 5 | Sprint 4 | done | TienPQ9 | US-14 | [6 empty] | Yes
US-10 | Discovery |  | As a learner, I want to search and filter courses so that I can find what I want. | Search by keyword; filter by category/price; paginated results. | Should | 5 | Sprint 2 | done | TungNT188 | US-05 | [6 empty] | Yes
US-11 | Discovery |  | As a learner, I want to view a course landing page and preview lesson (if have) so that I can decide before buying. | Shows description, curriculum, price and rating; free-preview lessons if any. | Must | 3 | Sprint 2 | done | TungNT188 | US-05 | [6 empty] | Yes
US-13 | Payment |  | As a learner, I want to create an order and be redirected to the payment gateway so that I can pay for a course. | Order created with a unique order_code; redirect to MoMo/VNPay; order stays pending until IPN confirms. | Must | 8 | Sprint 3 | done | TungNT188 | US-11 | [6 empty] | Yes
US-14 | Payment |  | As a learner,I want the system to automatically grant me course access right after my payment is successful,So that I can start learning immediately without waiting for manual approval. | Server-to-server IPN verified; duplicate IPN is idempotent (FR-PAY-03); enrollment created on success; browser redirect is not trusted for confirmation. | Must | 8 | Sprint 3 | done | TungNT188 | US-13 | [6 empty] | Yes
US-15 | Delivery |  | As a learner, I want lesson content served with access control so that only enrolled users can watch and links cannot be shared. | Content fetched via a short-lived signed URL ; HTTP Range requests supported for seeking; a non-enrolled user is denied. | Must | 13 | Sprint 3 | done | TienPQ9 | US-14 | [6 empty] | Yes
US-16 | Learning |  | As a learner, I want to study the lessons in a course I bought so that I can learn. | Enrolled learner opens the player and navigates sections/lessons; a non-enrolled user is blocked. | Must | 5 | Sprint 2 | done | DuongNT182 | US-15 | [6 empty] | Yes
US-17 | Progress |  | As a learner, I want my video progress tracked with resume so that I can pick up where I left off, and a completion % | current_position saved for resume; a lesson completes at >=90% watched; course % from completed lessons. | Must | 13 | Sprint 3 | done | TienPQ9 | US-16 | [6 empty] | Yes
US-18 | Reviews |  | As a learner, I want to rate and review a course so that others can judge it. | One review per enrolled learner; star + comment; course rating_avg updates. | Could | 3 | Sprint 4 | done | TungNT188 | US-16 | [6 empty] | Yes
US-19 | Learning |  | As a learner, I want to see the courses I have bought so that I can get back to them. | My-courses list of active enrollments, each with a resume link. | Should | 2 | Sprint 2 | done | TienPQ9 | US-14 | [6 empty] | Yes
US-20 | Quiz |  | As a learner, I want to take a quiz and get an automatic score so that I know how I did. | Submit answers; auto-graded; score and per-question result shown; attempt recorded. | Should | 5 | Sprint 3 | done | DuongNT182 | US-07 | [6 empty] | Yes
US-21 | Q&A |  | As a learner, I want to ask the instructor questions on a lesson so that I can clear doubts. | Post a question on a lesson; instructor replies; the thread is visible on the lesson. | Should | 1 | Sprint 4 | done | TungNT188 | US-16 | [6 empty] | Yes
US-22 | AI |  | As a learner, I want similar-course suggestions so that I discover relevant courses. | Recommendations from the learner profile/history; shown on course and home pages. | Should | 8 | Sprint 4 | done | DuongNT182 | US-11 | [6 empty] | Yes
US-23 | AI |  | As an instructor, I want AI to generate draft quiz questions from uploaded course materials so that I can prepare quizzes more quickly. | The system generates draft quiz questions based on the document, the instructor can review and edit the questions before using them. | Should | 5 | Sprint 4 | done | TienPQ9 | US-05
US-24 | AI |  | As an instructor, I want AI to suggest learning outcomes and create a curriculum draft so that I can plan a course more efficiently. | The instructor can request suggested learning outcomes for a course, the system generates a curriculum draft based on the available course information. | Should | 5 | Sprint 4 | done | TienPQ9 | US-05
Blue text = a formula rolled up from WBS on Story ID - do not type over it. Rows 2 to 5 are worked examples - delete them before you submit.

## WBS
Story ID | Task ID | Task | Assignee | Estimate (h) | Status | Note | Sprint | Task Type | Planned Start | Planned End | Actual (h) | Remain (h) | Blocked By | Reviewer | Done Date | Evidence (PR / commit)
| T-001 | Complete Project Proposal | TienPQ9 |  | done |  | Sprint 1
| T-002 | Initiate Backlog And WBS | TienPQ9 |  | done |  | Sprint 1
| T-003 | Initiate Database 01 | TungNT188 |  | done |  | Sprint 1
| T-004 | Initiate SRS v 01 | TienPQ9 |  | done |  | Sprint 1
| T-005 | Initiate HLD & LLD v01 | TungNT188 |  | done |  | Sprint 1
| T-006 | Project skeleton + users schema (V1) | DuongNT182 |  | done |  | Sprint 1
US-01 | T-012 | Registration: API + email verification | DuongNT182 |  | done |  | Sprint 1
US-01 | T-013 | Register screen (learner / instructor) | DuongNT182 |  | done |  | Sprint 1
US-04 | T-041 | Profile API + change password | DuongNT182 |  | done |  | Sprint 2
US-04 | T-042 | Profile view / edit screen + avatar, information,.. ( especially instructor need setup profile before create course) | DuongNT182 |  | done |  | Sprint 2
US-08 | T-081 | API: list instructor's own courses with status and enrollment count | TienPQ9 |  | done |  | Sprint 2
US-08 | T-082 | API: unpublish / republish a course | TienPQ9 |  | done |  | Sprint 2
US-08 | T-083 | Instructor "My Courses" screen | TienPQ9 |  | done |  | Sprint 2
US-05 | T-051 | Course CRUD API: title, description, thumbnail, price | TienPQ9 |  | done |  | Sprint 2
US-05 | T-052 | Create / edit course screen | TienPQ9 |  | done |  | Sprint 2
US-05 | T-053 | Draft / published state and owner-only edit check | TienPQ9 |  | done |  | Sprint 2
US-06 | T-061 | Create course with content, section, lesson | TienPQ9 |  | done |  | Sprint 2
US-06 | T-062 | Lesson CRUD API (video / text / file), stores storage_key | TienPQ9 |  | done |  | Sprint 2 |  |  |  |  | 0
US-06 | T-063 | Course content screen: section–lesson tree, drag to reorder | TienPQ9 |  | done |  | Sprint 2 |  |  |  |  | 0
US-10 | T-101 | Search API: keyword, category and price filters, pagination | TungNT188 |  | done |  | Sprint 2 |  |  |  |  | 0
US-10 | T-102 | Course list screen with filter bar | TungNT188 |  | done |  | Sprint 2 |  |  |  |  | 0
US-11 | T-111 | Course detail API: description, curriculum, price, rating | TungNT188 |  | done |  | Sprint 2 |  |  |  |  | 0
US-11 | T-112 | Mark lessons as free preview and serve preview content | TungNT188 |  | done |  | Sprint 2 |  |  |  |  | 0
US-11 | T-113 | Course landing page screen | TungNT188 |  | done |  | Sprint 2 |  |  |  |  | 0
US-16 | T-161 | API: course curriculum for enrolled learner (sections, lessons, current lesson) | TungNT188 |  | done |  | Sprint 2
US-16 | T-162 | Player screen layout: video area plus section–lesson sidebar | TungNT188 |  | done |  | Sprint 2
US-19 | T-191 | API: list active enrollments with course info and resume target | TungNT188 |  | done |  | Sprint 2
US-19 | T-192 | "My Courses" screen | TungNT188 |  | done |  | Sprint 2
US-02 | T-021 | Login + session/JWT + role-based authorization + lockout | DuongNT182 |  | done |  | Sprint 2
US-02 | T-022 | Login screen + error messages | DuongNT182 |  | done |  | Sprint 2
US-07 | T-071 | Migration and CRUD API for quiz, questions, options, correct answer | DuongNT182 |  | done |  | Sprint 3 |  |  |  |  | 0
US-07 | T-072 | Instructor quiz builder screen | DuongNT182 |  | done |  | Sprint 3 |  |  |  |  | 0
US-20 | T-201 | Quiz attempt API: submit answers, auto-grade, persist attempt | DuongNT182 |  | done |  | Sprint 3 |  |  |  |  | 0
US-20 | T-202 | Quiz-taking screen with score and per-question result | DuongNT182 |  | done |  | Sprint 3 |  |  |  |  | 0
US-13 | T-131 | Build signed payment request and redirect to payos | TungNT188 |  | done |  | Sprint 3 |  |  |  |  | 0
US-13 | T-132 | Buy button and payment-result screen reading order status | TungNT188 |  | done |  | Sprint 3 |  |  |  |  | 0
US-14 | T-141 | IPN endpoint: verify gateway signature, update order status | TungNT188 |  | done |  | Sprint 3 |  |  |  |  | 0
US-14 | T-142 | Create enrollment on successful payment | TungNT188 |  | done |  | Sprint 3 |  |  |  |  | 0
US-15 | T-151 | Generate short-lived HMAC-signed URL | TienPQ9 |  | done |  | Sprint 3 |  |  |  |  | 0
US-15 | T-152 | Two-phase delivery endpoint and wrire player to fetch signed url | TienPQ9 |  | done |  | Sprint 3 |  |  |  |  | 0
US-17 | T-171 | Heartbeat API: merge incoming bits with bitwise OR, save last position | TienPQ9 |  | done |  | Sprint 3 |  |  |  |  | 0
US-17 | T-172 | Mark lesson complete at ≥90% coverage; compute course completion % | TienPQ9 |  | done |  | Sprint 3 |  |  |  |  | 0
US-09 | T-091 | API: summarize paid revenue by instructor and course | TienPQ9 |  | done |  | Sprint 4 |  |  |  |  | 0
| T-092 | Instructor revenue dashboard and transaction list | TienPQ9 |  | done |  | Sprint 4 |  |  |  |  | 0
US-18 | T-181 | Review API: eligibility, create/update, and rating summary | TungNT188 |  | done |  | Sprint 4 |  |  |  |  | 0
US-18 | T-182 | Learner review form and course/instructor review views | TungNT188 |  | done |  | Sprint 4 |  |  |  |  | 0
US-21 | T-211 | Q&A API: lesson questions, answers, and course permissions | TungNT188 |  | done |  | Sprint 4 |  |  |  |  | 0
US-21 | T-212 | Learner lesson Q&A and instructor questions/reply screen | TungNT188 |  | done |  | Sprint 4 |  |  |  |  | 0
US-22 | T-221 | Recommendation API: continuous and Gemini suggestions | DuongNT182 |  | done |  | Sprint 4 |  |  |  |  | 0
US-22 | T-222 | -Learner recommendation sections and AI advisor UI | DuongNT182 |  | done |  | Sprint 4 |  |  |  |  | 0
US-24 | T-241 | Outcome suggestions and curriculum draft API | TienPQ9 |  | done |  | Sprint 4 |  |  |  |  | 0
US-24 | T-242 | Review and apply AI curriculum draft in authoring flow | TienPQ9 |  | done |  | Sprint 4 |  |  |  |  | 0
US-23 | T-231 | Generate quiz draft from supported course documents | TienPQ9 |  | done |  | Sprint 4 |  |  |  |  | 0
US-23 | T-232 | - Review, edit, and apply AI quiz draft in quiz authoring | TienPQ9 |  | done |  | Sprint 4 |  |  |  |  | 0
A-G are the task itself; H-Q are the planning, review and evidence columns. At the end of the sprint save the whole workbook as backlog_sprint<N>.xlsx - that one file is the sprint record (gate G1). Rows 2 to 15 are worked examples - delete them before you submit.

## Sprint Summary
Sprint summary - every number here is a formula over the WBS and Backlog sheets.
Member view sprint: |  | Sprint 2
Sprint | Stories | Points | Tasks | Est (h) | Actual (h) | Remain (h) | done | in-progress | todo | pending | % done (h)
Sprint 1 | 1 | 8 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0%
Sprint 2 | 8 | 44 | 22 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0%
Sprint 3 | 7 | 60 | 12 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0%
Sprint 4 | 7 | 32 | 12 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0%
Backlog | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Per member - for the sprint picked in C2
Member | Tasks | Est (h) | Actual (h) | Remain (h) | done | in-progress | todo | pending | Capacity (h) | Load
TienPQ9 | 9 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 30 | 0%
DuongNT182 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 30 | 0%
TungNT188 | 9 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 30 | 0%
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0%
<acc5> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0%
Capacity (h) is the only cell you type here: the hours that member really has in the sprint. Load over 100% means the sprint is over-committed - move a task out before the sprint starts, not on the last day.

## Master Data
Master data - the allowed values behind every dropdown in this workbook.
Status, Priority, Points, Risk and Type are fixed by the brief - do not rename them. Assignee and Sprint are yours: put in your team and check the dates against submission_guide.md.
Status | When to use it | Note required? | Priority | Meaning (MoSCoW) | Points | Sprint | Start | End | Deadline | Assignee | Full name | Role in the team | Task Type | Story Type | Risk | Meaning | Yes/No | ID format | Example | Rule
todo | Planned, nobody has started it yet. | Only when it is waiting on something, or was added after the freeze. | Must | Ship it or the product does not work. | 1 | Sprint 1 | 2026-08-13 | 2026-08-19 | 2026-08-19 23:59 | TienPQ9 | Phung Quang Tien | Frontend / Backend | Analysis | Feature | Low | Known ground, no unknowns left. | Yes | Story ID | US-01 | US- plus two digits. One row per story on the Backlog sheet.
in-progress | Someone is working on it right now. | Yes - name the concrete step you are on. | Should | Important, but the sprint survives without it. | 2 | Sprint 2 | 2026-08-20 | 2026-08-25 | 2026-08-25 23:59 | DuongNT182 | Nguyễn Tùng Dương | Frontend / Backend | Design | Tech | Medium | One unknown - a library or an API nobody used yet. | No | Task ID | T-011 | T- plus story number plus a task number: T-011 is task 1 of US-01.
done | Merged into the default branch and it works. | Optional - evidence, or the scope you cut. | Could | Nice to have if there is time left. | 3 | Sprint 3 | 2026-08-26 | 2026-09-04 | 2026-09-04 23:59 | TungNT188 | Nguyễn Thanh Tùng | Frontend / Backend | Database | Bug | High | Technical hard core, or a third-party the team cannot control. |  | Account | AlexDF | First name plus the initials of the remaining parts: Alex De Fleu.
pending | Started or planned, then stopped. | Yes - why it stopped and what unblocks it. | Won't | Agreed out of scope for this release. | 5 | Sprint 4 | 2026-09-07 | 2026-09-11 | 2026-09-11 23:59 |  |  |  | Backend | Spike
[5 empty] | 8 | Backlog |  |  | Not scheduled yet | <acc5> | <full name> | <role> | Frontend | Chore
[5 empty] | 13 | [7 empty] | Integration
Test
Docs
DevOps
Spike
Bugfix

## Guide
What is in this workbook
Backlog | One row per user story - the story, its acceptance criteria, priority, size, owner, risk and the sprint that owns it. Tasks / Est / Actual / Remain / Progress are formulas rolled up from WBS on Story ID.
WBS | One row per task. A-G are the task itself - story, id, name, owner, estimate, status, note; H-Q are the planning, review and evidence columns D02 asks for: the plan, the actual result, and who contributed what.
Sprint Summary | Read-only roll-up: per sprint and per member. Pick the sprint in cell C2, type each member's real Capacity (h), and the Load column tells you who is over-committed.
Master Data | Every dropdown reads from here, plus the ID formats. Replace the Assignee list with your team; leave Status, Priority, Points, Risk and Type alone.
IDs
Story ID | US- plus two digits (US-01). Lives on the Backlog sheet; the WBS Story ID column is a dropdown of those IDs.
Task ID | T- plus the story number plus a task number: T-011 is task 1 of US-01, T-023 is task 3 of US-02. Unique across the project - the sprint review record and your commit messages refer to it.
Task | Just the name, no ID in it: 'Double-booking check API'.
Account | First name plus the initials of the remaining parts - Alex De Fleu becomes AlexDF.
Filling it in
Blue text | A formula. Typing over one breaks the roll-up - everything else on Backlog and WBS is yours to fill in.
Yellow cells | Only on Sprint Summary: Capacity (h), the one thing you type on that sheet.
Example rows | Backlog rows 2-5 and WBS rows 2-15 are worked examples. Delete every one before you submit.
Story <-> task link | The roll-up matches WBS Story ID against Backlog Story ID exactly. Use the dropdown; a hand-typed 'US-1' silently shows 0 tasks.
One owner per task | Assignee takes exactly one name. A task nobody owns counts as missing at gate G1.
Remain (h) | A formula: 0 once the task is done, otherwise Estimate minus Actual. Sum it per sprint for your burndown.
Status - the only four values
todo | Planned, not started.
in-progress | Being worked on right now.
done | Merged into the default branch and working.
pending | Started or planned, then stopped. Not the same as todo - somebody is waiting on something.
What goes in the Note column
todo | Usually empty. Write a note only when it is waiting on something: 'Not started - starts when T-012 is merged'.
in-progress | Always. Name the concrete step, not the status: 'Slot query done; writing the overlap check in AppointmentService'. 'Implementing' says nothing.
done | Empty when it shipped as planned. Add evidence ('Merged in PR #34 with 6 unit tests') or the scope you cut ('Reduced scope - email only; SMS moved to T-034').
pending | Always. Why it stopped, since when, and what unblocks it: 'Blocked - no sandbox credentials from the SMS provider yet'. For carry-over, add the hours spent and the branch.
Added <YYYY-MM-DD> | Required by gate G1 on any task added after the freeze. It goes first in the Note, then the description - and the same change must appear in sprint<N>_review.md as a scope change.
Submitting for gate G1
1 | Freeze the backlog before the sprint starts: every task planned, owned and estimated.
2 | Anything added after the freeze carries Added <YYYY-MM-DD> first in its Note, and shows up in sprint<N>_review.md as a scope change.
3 | At the end of the sprint, File > Save a Copy as backlog_sprint<N>.xlsx. One file per sprint - there is no open/close pair.
4 | Upload it to <CLASS>/<TEAM>/Sprint <N>/ on Drive and leave it alone: that copy is the frozen record. The Drive upload time is the submission time - see submission_guide.md.